## Title
|  |  |  | Issue No. |  | A
|  |  |  | Issue Date |  | 2025-04-16
|  |  |  | Originator |  | H. Adefuwa
Project Details | Project Serial No.: |  | DP0064
| Project: |  | Maintenance on Closed Loop Systems
| Product Code: |  | IM0004
| Rev: |  | 1
Project Serial No.: IM0004
Document Title: IM0004 Electrical Test Procedure
Electrical Drawing Title: IM0004 Electrical Drawings Rev1
Electrical Drawing Revision: 1
Document Revision Table
Rev | Date | Description | Author | Checked | Approved
1 | 2025-05-19 | First Issue | 2025-05-19 | - | -
|  |  | HA | - | -
2 | 2026-01-21 | Post-Handover | 2026-01-21 | - | -
|  |  | HA | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
Notes
Serial Number

## Test Procedure
Step | Criteria | Comments | Pass/Fail (✓/X) | Sign Off
1. Documentation Verification
1.1 | Verify that you have the latest Electrical drawings - as mentioned on the front of this document.
1.2 | Ensure all documents are the latest revisions and properly approved.
1.3 | Have Electrical wiring drawings available, along with a suffecient means of marking the drawings, such as a green highlighter.
1.4 | Ensure all test equipment to meet the applicable regulations. IEC/EN 61010-1 (Cat III 600V Minimum)
2. Visual Inspection
2.1 | Check that the product is free from any physical damage and is in a good clean condition.
2.2 | Ensure that all labels, tags, and nameplates are correctly installed and legible.
2.3 | Confirm that all components are properly mounted and secure. Ensure all DIN rails have the appropriate End Stops installed to prevent components from sliding off.
2.4 | Confirm power input (DC barrel jack) is correctly fused and marked "24V DC ONLY".
2.5 | Confirm all wires are labelled and have a wire number. Checking accuracy of these numbers will be done later.
2.6 | Confirm Terminals X1, X2, and X3 have the correct jumper bars installed. Shown on sheet 7 & 8 of the drawings.
Step | Criteria | Comments | Pass/Fail (✓/X) | Sign Off
3. Preperation & Dead Testing
3.1 | Verify PSU is not connected. No LED indicators should be lit.
3.2 | Ensure all circuit breakers, namely MCB1, is turned off. The status colour strip on the breaker should be green with the switch in the down position.
3.3 | Confirm the tank is empty of water, if not, drain tank.
3.4 | Ensure Emergency Stop is not pressed, and that the button is reset in the up position.
3.5 | Perform cable pull test on all removable wires, front and back of panel. Ensure all wires are mechanically terminated correctly.
3.6 | Perform a green line test on the 24V circuits, checking wire continuity is correct and then marking the drawings with a green highlighter. The 24V circuits are (L1 and L2) outlined on sheet 2 of the drawings. Ensure correct continuity on both the 24V and 0V wires. Mark the physical drawings with your results.
3.7 | Confirm MCB1 is wired correctly, from fuse on X0-1, by performing a continuity test, as shown on sheet 7. Mark drawings.
3.8 | Work through the rest of the drawings, conducting a green line test on all 24V circuits (L1 and L2) on each sheet. Regarding DRV1 & DRV2, these spade terminals are insulated and as such you will need to partially remove them to test continuity. Ensure you push them back on after test. Correct continuity here is vital.
Step | Criteria | Comments | Pass/Fail (✓/X) | Sign Off
3.9 | Starting with the digital inputs on sheet 3, verify the wiring of the emergency stop. Press the emergency stop. Perform a continuity test on all the wiring S1 & S2. One side of each of the outer modules, should be wired to terminals X1. The other side should be wired to the first and second input on the PLC (0 & 1). Mark the drawings and reset the emergency stop.
3.1 | Perform the same test for the blue reset button S3. No need to press this button. Mark drawings.
3.11 | Conduct a continuity test between the terminals on X3 and their accompanying pin on connector CN2. Confirm continuity between X3-1 and CN2-1. Repeat for the other terminals on X3. Mark drawings. Use the Connector Layout sheet to assist.
3.12 | Complete basic continuity test on sheet 5, PLC outputs. There are no male/female connectors for these wires. For the H2 Status LED, you cannot test continuity so confirm the wire colours are correct at the PLC end. Blue to 0V at X3-6 and then black, brown and white to the PLC outputs.
3.13 | Confirm network/ethernet cable is installed corrrectly as shown on sheet 10.
3.14 | Only proceed onto the next section if continuity tests are correct.
4. Power-Up Sequence
4.1 | Ensure the tank is connected to the rig and plugged in.
Step | Criteria | Comments | Pass/Fail (✓/X) | Sign Off
4.1 | Use a 24V power supply unit (PSU) of atleast 2A minimum current. Confirm the circuit breaker MCB1 is off and plug in the PSU's DC barrel into the socket at the back of the training rig. Confirm nothing has turned on, no lights should be on.
4.2 | Turn on MCB1, you should now see many components power on.
4.3 | Confirm the PLC and its module (attached to the right) has turned on.
4.4 | Confirm the HMI has turned on.
4.5 | Confirm the temperature sensor LED is on.
4.6 | Turn the power off to program the PLC using the SD card. Insert the SD card. Power on the system. The “RUN/STOP” lamp will then flash for a period and then the “MAINT” lamp will start flashing. Power off the system. Remove the SD card. Power on the system, wait a minute and confirm PLC output LEDs (the ones at the bottom) are flashing. The “RUN/STOP” LED on the PLC must be steady green.
4.7 | With the power on, check the firmware version of the HMI. This is done by selecting the third option on the left, system properties. You then select "Panel Information" and look at the Runtime version. If the runtime version does not state V20.X.X.X then it must be updated. This is done using the IM0004 USB stick. Select the Service and Commissioning button on the HMI, bottom of the left menu. Select Update OS. Scroll down and click on UBP_4_12_V20_0.fwf and then click Update OS button at the bottom and click OK on the popup alert. Then wait 5 minutes whilst the HMI reboots and upgrades. It is essential that power is kept on this entire time, do not use the rig during this process. Once the HMI has booted back into the standard menu, then proceed.
4.8 | With the power on. Program the HMI using the USB stick. Insert the USB into the back of the HMI, if you have not already done so. Select Runtime Properties, the 4th button in the menu on the left. Select Load project from storage. Select the USB stick in the dropdown menu. Click on HMI_RT in the projects on external storage table. Scroll down and press "Load project." If asked for a password, enter "Matrix123?".
4.9 | Select the System Properties and the Display option and increase the brightness to 100%.
4.10 | Select the Runtime Properties again and select Automatic runtime start. Set the waiting time value to 0. Restart power to the training rig.
4.11 | Confirm HMI boots into the Matrix software upon reboot. Remove USB stick.
4.12 | Confirm the status LED has turned on, likely it will be red, but any colour is acceptable at this stage.
Step | Criteria | Comments | Pass/Fail (✓/X) | Sign Off
5. Functional Testing
5.1 | Fill the tank with approximately 4 litres of water and secure the lid to the tank.
5.2 | Navigate to the Faults screen of the HMI. Main Menu > Faults. Press the reset button and confirm you have no faults. If faults are present, begin troubleshooting. The User Manual can help you here.
5.3 | If no faults, press the emergency stop and confirm the status LED turns red.
5.4 | Reset the fault and confirm the status LED becomes green again.
5.5 | Check the proximity sensor LED is on whilst the tank lid is on. Apply a small amount of pressure to the tank bracket under the proximity sensor, should not immediately tunr off the proximity sensor LED. If it does, please adjust the proximity sensor lower down towards the bracket.
6. Load Testing
6.1 | Ensure the hand/gate valve is open, turn fully anti-clockwise, then run the system by pressing the Start button on the HMI. Main Menu > Start Program > Start
6.2 | Confirm the pump is running.
6.3 | Confirm the HMI setpoint is 150 and that the physical gauge on the training rig is reading roughly 150 after a 5-10 seconds. If there is no flow, there may be air locked in the system. To release this, unclip the latches that hold the valve assembly to the lid and tilk it 45 degrees anti-clockwise, whilst the pump is running.
Step | Criteria | Comments | Pass/Fail (✓/X) | Sign Off
6.4 | Shut the hand/gate valve by turning fully clockwise and confirm the flow drops to 0. Leave the system running for 5 minutes.
6.5 | Confirm after roughly 10-20 seconds, the system shuts off and a fault occurs. Reset the fault and open the hand/gate valve.
6.6 | Don't run the system again, instead press the Valve Overide button on the bottom right of the Operator Screen, this will help drain water out of the pipes. You may need to unclip the latches that hold the valve assembly to the lid and tilt the assembly 45 degrees anti-clockwise to aid in draining the system.
6.7 | Once the pipes are drained of water, turn off the valve overide on the screen, turn off the circuit breaker MCB1 and empty the tank.
7. Documentation
7.1 | Note any discrepancies, comments or issues on the final page of this test procedure and rectify as required.
7.2 | Sign off on the test procedure, confirming that all tests have been performed and that the product is functional and safe to use.

## Signature
Test Status |  |  | Comments
1 | ACCEPTED As Final
2 | ACCEPTED Product shipment may proceed, Incorporate Comments
3 | REJECTED Product shipment may not proceed, Incorporate Comments
Test Summary
On Behalf Of: | Production Staff | Matrix TSL |  | Third Party
Date: