## Title
|  |  |  | Issue No. |  | A
|  |  |  | Issue Date |  | 2025-04-16
|  |  |  | Originator |  | H. Adefuwa
Project Details | Project Serial No.: |  | DP0062
| Project: |  | Locktronics - PLC LOGO Board
| Project Description: |  | Locktronics PLC Module with Siemens LOGO!
| Rev: |  | 1
Project Serial No.: IM3214
Document Title: IM3214 Electrical Test Procedure
Electrical Drawing Title: Electrical Drawings IM3214-B.pdf
Revision: B
Document Revision Table
Rev | Date | Description | Author | Checked | Approved
A | 2025-04-16 | First Issue | 2025-04-16 | - | -
|  |  | HA | - | -
B | 2025-09-25 | Revised | 2025-09-25 | - | -
|  |  | HA | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
Notes

## Test Procedure
Step | Criteria | Comments | Pass/Fail (✓/X) | Sign Off
1. Documentation Verification
1.1 | Verify that electrical & mechanical drawings are available.
1.2 | Ensure all documents are the latest revisions and properly approved.
1.3 | Ensure all test equipment to meet the applicable regulations. IEC/EN 61010-1 (Cat III 600V Minimum)
2. Visual Inspection
2.1 | Check that the product is free from any physical damage and is in a good clean condition.
2.2 | Ensure that all labels, tags, and nameplates are correctly installed and legible.
2.3 | Confirm that all components are properly mounted and secure.
2.4 | Ensure the PLC does not slide off from the DIN Rail and that the End Stops are secure and correctly stop the PLC from moving.
2.5 | Visually inspect the Locktronics legs, ensure they all look aligned.
3. Preperation & Dead Testing
3.1 | Ensure the LOGO! Is powered off and disconnected from 24V and that no LEDs are on.
3.2 | Place the PLC Module into a Locktronics baseboard. Ensure the legs can be secured into the baseboard and that the product sits well.
Step | Criteria | Comments | Pass/Fail (✓/X) | Sign Off
3.3 | Remove the PLC Module from the baseboard. Conduct a pull test on each cable on the PLC. Ensure the cables are secured into the PLC.
3.4 | Check electrical continuity of each leg to the accompanying PLC terminal with a multimeter. Use the Electrical wiring diagram (sheet 2) to support you in this. For example, the top right leg should have continuity to the I5 terminal screw on the PLC.
3.5 | Only proceed onto the next section if continuity tests are correct.
4. Power-Up Sequence
4.1 | Use a 24V power supply unit (PSU), either a DC barrel with a Locktronics component or a benchtop power supply. Ensure the PSU can do more than 1A. A Locktronics baseboard is necessary here.
4.2 | Place 24V on the (+) and 0V on the (-). Top left and bottom left respectively. Confirm the green LED (+), in the top left illuminates.
4.3 | Confirm the LOGO! PLC has turned on. The screen/hmi should be illuminated.
5. Functional Testing
5.1 | Place a 4mm cable from the (+) pillar to the input 1 (I1). Confirm the LED turns on. Repeat this for I2, I3, I4 and I5.
Step | Criteria | Comments | Pass/Fail (✓/X) | Sign Off
5.2 | Place a 4mm cable between the (+) pillar and (Q1). Confirm the LED turns on. Repeat this for Q2, Q3 and Q4. Remove this connector when complete.
6. Load Testing
6.1 | Remove the Micro SD card from the LOGO!. You may need to use a screw driver to open the SD card slot. Be aware, the SD card slot is not fully removeable.
6.2 | Insert the Micro SD card into your computer and copy Program 1 onto the SD card. Overwrite the file if there is one present. Note the file will be in a folder called Worksheet 1 but the file you need will be called LOGO_U_P.bin
6.3 | Install the Micro SD Card back into the LOGO!. Take note of the direction of insertion, the pull out tab has a diagram underneath it to aid in correct insertion.
6.4 | Start the Program on the LOGO! by navigating to Card > Load program and follow the on-screen instructions to load the binary file into the controller.
6.5 | Confirm you can see the output LEDs turning on and off.
7. Documentation
7.1 | Add serial number to the bottom of the LOGO!
7.2 | Note any discrepancies, comments or issues on the final page of this test procedure and rectify as required.
7.3 | Sign off on the test procedure, confirming that all tests have been performed and that the product is safe to use.

## Signature
Test Status |  |  | Comments
1 | ACCEPTED As Final
2 | ACCEPTED Product shipment may proceed, Incorporate Comments
3 | REJECTED Product shipment may not proceed, Incorporate Comments
Test Summary
Serial Number:
Works Order:
On Behalf Of: | Production Engineer | Matrix TSL |  | Third Party